## Sheet1
Risk Description | Likelihood | Severity | Risk Exposure | Assigned To) | No | Description
Software too small | 30% | 1 | 16 hr | Rafael Olivares | 1 | Catastrophic
Browser doesn't support the software | 10% | 4 | 1 hr | Minseok Kim | 2 | Critical
Files too big | 70% | 1 | 8 hr | Rafael Olivares | 3 | Marginal
Time to response email is longer | 40% | 3 | 2 hr | Minseok Kim | 4 | Negligible
Internet connection will be lost | 10% | 3 | 1 hr | Phu Quy Tran
Lack of back up database | 20% | 1 | 24 hr | Phu Quy Tran